## Sheet1
UTC TIME REFERENCE | Orbit Time (h:mm:ss) | Time Since Previous Event (sec) | Lat. (deg) | Long. (deg) | Altitude (km) | POMONKEY | GOLDSTONE | CANBERRA | MADRID | Sun Shadow | Site | Orbital Event | S/C Command Activities | UV/Vis | HiRes | NIR | LWIR | Laser | Comment
1994-03-11 15:27 | 0:00 |  | 28 | 23 | 2951.8 | [6 empty] | Aposelene | [6 empty] | Downlinking SSDR Segment 5 (orbit 93)
1994-03-11 15:32 | 0:05 | [11 empty] | Downlink SSDR Segment 6 | [5 empty] | Ground Commmand
1994-03-11 15:41 | 0:13 |  | 20 | 22.9 | 2924.9 | [6 empty] | N20D
1994-03-11 15:45 | 0:18 |  | 17.4 | 22.9 | 2904.7 | [6 empty] | INPM | [6 empty] | Enter penumbra
1994-03-11 15:46 | 0:19 |  | 16.8 | 22.9 | 2899.1 | [6 empty] | INUM | [6 empty] | Enter umbra
1994-03-11 15:57 | 0:30 |  | 10 | 22.8 | 2819.2 | [6 empty] | N10D
1994-03-11 16:03 | 0:36 | [11 empty] | Downlink SSDR Segment 7 | [5 empty] | Ground Commmand
1994-03-11 16:12 | 0:45 |  | 0 | 22.7 | 2646.5 | [6 empty] | Equator - D
1994-03-11 16:26 | 0:59 |  | -10 | 22.6 | 2426.4 | [6 empty] | S10D
1994-03-11 16:39 | 1:12 |  | -20 | 22.5 | 2180.1 | [6 empty] | S20D
1994-03-11 16:46 | 1:18 |  | -26 | 22.5 | 2028.5 | [6 empty] | OUTUM | [6 empty] | Exit umbra
1994-03-11 16:47 | 1:19 |  | -26.7 | 22.5 | 2008.7 | [6 empty] | OUTPM | [6 empty] | Exit penumbra
Standard Prep1 Script
1994-03-11 16:48 | 1:20 | 0 | [10 empty] | NIR camera & cryocooler ON; SA mode to AUTO
End Prep1 Script
1994-03-11 16:50 | 1:23 |  | -30 | 22.5 | 1926.3 | [6 empty] | S30D
1994-03-11 17:00 | 1:32 |  | -40 | 22.4 | 1679.2 | [6 empty] | S40D
Standard Prep2 Script
1994-03-11 17:02 | 1:35 | 0 | [10 empty] | LWIR camera & cryocooler ON; Laser heater ON; Open sensor door if closed
End Prep2 Script
#VALUE!
1994-03-11 17:07 | 1:40 | 0 | [10 empty] | Msg "WRNG: Omni/2k in 1 min.."
1994-03-11 17:08 | 1:41 | 60 | [10 empty] | SSDR to IDLE; Switch to 2 kbps bypass mode
1994-03-11 17:08 | 1:41 |  | -50 | 22.4 | 1448.6 | [6 empty] | S50D
1994-03-11 17:09 | 1:42 | 60 | [10 empty] | Switch to omni antennas
1994-03-11 17:10 | 1:43 | 60 | [10 empty] | Select ST-A; Set SA step rate to HI; Slew s/c sensors to Crux (ACSMode=StarPointing, Index=3) | [5 empty] | Slew to Crux
1994-03-11 17:10 | 1:43 | 30 | [10 empty] | UV & HR cameras ON
1994-03-11 17:13 | 1:46 | [9 empty] | MAD | LOS
1994-03-11 17:15 | 1:48 |  | -60 | 22.5 | 1239.9 | [6 empty] | S60D
1994-03-11 17:17 | 1:50 | [11 empty] | Ranging B OFF; Ranging A ON | [5 empty] | Ground Commmand
1994-03-11 17:19 | 1:52 | 545 | [10 empty] | Initialize filters (DHU SEQT 28); Record in SSDR Segment 1; Load lunar dark exposure tables | [5 empty] | Start SSDR in Segment 1
1994-03-11 17:20 | 1:53 | 25 | [10 empty] | Perform NIR imaging (DHU SEQT 31) | [5 empty] | Dark Field imaging starts
1994-03-11 17:20 | 1:53 | 15 | [10 empty] | Stop imaging - select ST-A
1994-03-11 17:22 | 1:54 |  | -70 | 22.6 | 1055.8 | [6 empty] | S70D
1994-03-11 17:22 | 1:55 | 105 | [10 empty] | Perform LWIR imaging (DHU SEQT 25)
1994-03-11 17:22 | 1:55 | 15 | [10 empty] | Perform NIR imaging (DHU SEQT 31)
1994-03-11 17:22 | 1:55 | 15 | [10 empty] | #VALUE! | [5 empty] | Slew to nadir (inertial pointing)
1994-03-11 17:23 | 1:56 | 30 | [10 empty] | Laser Power ON
#VALUE!
1994-03-11 17:27 | 2:00 |  | -80 | 23.1 | 896.9 | [6 empty] | S80D
#VALUE!
1994-03-11 17:30 | 2:03 | 0 | [10 empty] | Initialize filters (DHU SEQT 28); Load exposure table LUNARZ85S | [5 empty] | NOTE: Pre-burn state vector being used on s/c. Position off by 150 km!
1994-03-11 17:31 | 2:04 | 60 | [10 empty] | Switch to lunar mapping mode (ACSMode=LunarMapping); Start imaging (DHU SEQT 9) | [5 empty] | START MAPPING
1994-03-11 17:32 | 2:05 |  | -89.8 | 111.1 | 762.5 | [6 empty] | South Pole
1994-03-11 17:32 | 2:05 | 60 | [9 empty] | MAXS | Set SA step rate to LO
1994-03-11 17:33 | 2:06 |  | -88.6 | 194.7 | 745.4 | [6 empty] | LDAWN
1994-03-11 17:37 | 2:10 |  | -80 | 200.9 | 651.4 | [6 empty] | S80A
1994-03-11 17:37 | 2:10 | 275 | [9 empty] | S80A | Load exposure table LUNARZ75S; Select DHU SEQT 3
1994-03-11 17:41 | 2:14 |  | -70 | 201.4 | 562.2 | [6 empty] | S70A
1994-03-11 17:41 | 2:14 | 252 | [9 empty] | S70A | Load exposure table LUNARZ65S; Select DHU SEQT 4
1994-03-11 17:45 | 2:18 |  | -60 | 201.6 | 493.7 | [6 empty] | S60A
1994-03-11 17:45 | 2:18 | 236 | [9 empty] | S60A | Load exposure table LUNARZ55S; Select DHU SEQT 6
1994-03-11 17:49 | 2:21 |  | -50 | 201.6 | 444.7 | [6 empty] | S50A
1994-03-11 17:49 | 2:21 | 224 | [9 empty] | S50A | Record in SSDR Segment 2; Park opaque filter on HiRes (DHU SEQT 27) | [5 empty] | SSDR Segment 2
1994-03-11 17:49 | 2:22 | 10 | [10 empty] | Load exposure table LUNARZ45S; Select DHU SEQT 5
1994-03-11 17:50 | 2:23 | [9 empty] | GDS | MLOSM
1994-03-11 17:50 | 2:23 | [9 empty] | PMK | MLOSM | [6 empty] | Enter occultation
1994-03-11 17:51 | 2:23 | 103 | [9 empty] | S40A | Load exposure table LUNARZ35S | [5 empty] | Delay wrong in orig. timeline - should be 235 sec.
1994-03-11 17:52 | 2:25 |  | -40 | 201.7 | 414.2 | [6 empty] | S40A
1994-03-11 17:54 | 2:27 | 212 | [9 empty] | S30A | Load exposure table LUNARZ25S
1994-03-11 17:56 | 2:29 |  | -30 | 201.7 | 401.7 | [6 empty] | S30A
1994-03-11 17:57 | 2:29 |  | -28 | 201.7 | 401.4 | [6 empty] | Periselene
1994-03-11 17:58 | 2:30 | 210 | [9 empty] | S20A | Load exposure table LUNARZ15S
1994-03-11 17:59 | 2:32 |  | -20 | 201.7 | 407 | [6 empty] | S20A
1994-03-11 18:01 | 2:34 | 214 | [9 empty] | S10A | Load exposure table LUNARZ05S; Select DHU SEQT 6
1994-03-11 18:03 | 2:36 |  | -10 | 201.7 | 430.1 | [6 empty] | S10A
1994-03-11 18:05 | 2:38 | 220 | [9 empty] | MEQA | Record in SSDR Segment 3; Load exposure table LUNARZ05N; Select DHU SEQT 7 | [5 empty] | SSDR Segment 3
1994-03-11 18:07 | 2:39 |  | 0 | 201.7 | 471.5 | [6 empty] | Equator - A
1994-03-11 18:09 | 2:41 | 230 | [9 empty] | N10A | Load exposure table LUNARZ15N; Select DHU SEQT 8
1994-03-11 18:10 | 2:43 |  | 10 | 201.7 | 532 | [6 empty] | N10A
1994-03-11 18:13 | 2:46 | 245 | [9 empty] | N20A | Load exposure table LUNARZ25N; Select DHU SEQT 9
1994-03-11 18:14 | 2:47 | 60 | [10 empty] | Laser power OFF
1994-03-11 18:14 | 2:47 |  | 20 | 201.7 | 612.5 | [6 empty] | N20A
1994-03-11 18:17 | 2:50 | 205 | [9 empty] | N30A | Load exposure table LUNARZ35N; Select DHU SEQT 10
1994-03-11 18:19 | 2:52 |  | 30 | 201.7 | 714.4 | [6 empty] | N30A
1994-03-11 18:22 | 2:55 | 290 | [9 empty] | N40A | Record in SSDR Segment 4; Load exposure table LUNARZ45N; Select DHU SEQT 11 | [5 empty] | SSDR Segment 4
1994-03-11 18:24 | 2:56 |  | 40 | 201.7 | 839.1 | [6 empty] | N40A
1994-03-11 18:25 | 2:58 | 193 | [9 empty] | N50A | Load CEQ_12U.UMI into SEQT 12; Load exposure table LUNARZ55N; Select DHU SEQT 12 | [5 empty] | IR and UV uncompressed (nearly 4 minutes early)
1994-03-11 18:26 | 2:59 | [9 empty] | PMK | MAOSM | [6 empty] | Exit occultation
1994-03-11 18:26 | 2:59 | [9 empty] | GDS | MAOSM
1994-03-11 18:27 | 3:00 | [11 empty] | Ranging A OFF | [5 empty] | Ground Commmand
1994-03-11 18:29 | 3:02 |  | 50 | 201.7 | 987.9 | [6 empty] | N50A
1994-03-11 18:31 | 3:04 | 363 | [9 empty] | N60A | Load exposure table LUNARZ65N; Select DHU SEQT 13 | [5 empty] | Resume compression
1994-03-11 18:35 | 3:08 |  | 60 | 201.7 | 1161.7 | [6 empty] | N60A
1994-03-11 18:38 | 3:11 | 413 | [9 empty] | N70A | Load exposure table LUNARZ75N; Select DHU SEQT 14
1994-03-11 18:42 | 3:15 |  | 70 | 201.8 | 1360.4 | [6 empty] | N70A
1994-03-11 18:46 | 3:19 | 473 | [9 empty] | N80A | Load exposure table LUNARZ85N; Select DHU SEQT 15
1994-03-11 18:47 | 3:20 | 60 | [10 empty] | Load DEQ_12.UMI into SEQT12 | [5 empty] | Restore compressed SEQT 12
#VALUE!
1994-03-11 18:50 | 3:23 |  | 80 | 202.3 | 1582.5 | [6 empty] | N80A
1994-03-11 18:59 | 3:32 |  | 89.8 | 289.2 | 1823.6 | [6 empty] | North Pole
#VALUE!
1994-03-11 19:00 | 3:33 | 0 | [10 empty] | Set SA step rate to HI; Select ST-A; Slew s/c sensors to Vega (GNC12VEGA); Laser power OFF; Load dark images exposure table | [5 empty] | Slew to Vega (inertial pointing)
1994-03-11 19:00 | 3:33 |  | 88.6 | 13.9 | 1858.8 | [6 empty] | LDUSK
1994-03-11 19:09 | 3:42 |  | 80 | 20.1 | 2076.2 | [6 empty] | N80D
1994-03-11 19:10 | 3:43 | 600 | [10 empty] | Perform UV0 imaging (DHU SEQT 29) | [5 empty] | Radiometric imaging starts
1994-03-11 19:10 | 3:43 | 15 | [10 empty] | Perform LWIR imaging (DHU SEQT 25) | [5 empty] | Dark Field imaging starts
1994-03-11 19:11 | 3:43 | 15 | [10 empty] | Perform NIR imaging (DHU SEQT 31)
1994-03-11 19:11 | 3:44 | 15 | [10 empty] | Perform HR imaging (DHU SEQT 30)
1994-03-11 19:11 | 3:44 | 7 | [10 empty] | Stop imaging - select ST-A; UV & HR cameras OFF; IR cameras & cryocoolers OFF; Slew s/c HGA to Earth (ACSMode=EarthPointing, Center) | [5 empty] | Slew HGA to Earth
1994-03-11 19:17 | 3:50 | 360 | [10 empty] | Switch to HGA | [5 empty] | READY FOR DATA DUMP
#VALUE!
1994-03-11 19:17 | 3:50 | [11 empty] | Switch to DHU mode @ 128 kbps | [5 empty] | Ground Command
1994-03-11 19:18 | 3:51 | [11 empty] | Downlink SSDR Segment 1 | [5 empty] | Ground Command
1994-03-11 19:21 | 3:54 |  | 70 | 20.5 | 2327.5 | [6 empty] | N70D
1994-03-11 19:30 | 4:03 | [11 empty] | Update state vector (GNC53_11MAR1920) | [5 empty] | Ground Command Error reduced from 150km to 10m
1994-03-11 19:35 | 4:07 |  | 60 | 20.6 | 2560.7 | [6 empty] | N60D
1994-03-11 19:49 | 4:22 | [11 empty] | Downlink SSDR Segment 2 | [5 empty] | Ground Command
1994-03-11 19:50 | 4:22 |  | 50 | 20.5 | 2755.1 | [6 empty] | N50D
1994-03-11 19:55 | 4:28 | [11 empty] | Uplink & schedule L095 scripts | [5 empty] | Ground Command
1994-03-11 20:06 | 4:38 |  | 40 | 20.4 | 2889.9 | [6 empty] | N40D
1994-03-11 20:17 | 4:50 | [11 empty] | Downlink SSDR Segment 3 | [5 empty] | Ground Command
1994-03-11 20:22 | 4:55 |  | 30 | 20.3 | 2948.7 | [6 empty] | N30D
1994-03-11 20:26 | 4:58 |  | 28 | 20.3 | 2950.5 | [6 empty] | Aposelene