## Sheet1
UTC TIME REFERENCE | Orbit Time (h:mm:ss) | Time Since Previous Event (sec) | Lat. (deg) | Long. (deg) | Altitude (km) | POMONKEY | GOLDSTONE | CANBERRA | MADRID | Sun Shadow | Site | Orbital Event | S/C Command Activities | UV/Vis | HiRes | NIR | LWIR | Laser | Comment
1994-03-24 01:50 | 0:00 |  | 28.9 | 219 | 2917.4 | [6 empty] | Aposelene | [6 empty] | Downlink SSDR Segment 7 (orbit 153)
1994-03-24 02:03 | 0:13 |  | 21.1 | 218.9 | 2892.5 | [6 empty] | INPM | [6 empty] | Enter penumbra
1994-03-24 02:03 | 0:14 |  | 20.6 | 218.9 | 2889.1 | [6 empty] | INUM | [6 empty] | Enter umbra
1994-03-24 02:04 | 0:15 |  | 20 | 218.9 | 2885.3 | [6 empty] | N20D
1994-03-24 02:20 | 0:31 |  | 10 | 218.9 | 2777.7 | [6 empty] | N10D
1994-03-24 02:35 | 0:46 |  | 0 | 218.8 | 2607.5 | [6 empty] | Equator - D
1994-03-24 02:44 | 0:54 | [11 empty] | SSDR to IDLE - downlink complete | [5 empty] | Ground Command
1994-03-24 02:49 | 0:59 |  | -10 | 218.8 | 2393.2 | [6 empty] | S10D
1994-03-24 03:01 | 1:12 |  | -20 | 218.8 | 2154.6 | [6 empty] | S20D
1994-03-24 03:11 | 1:22 |  | -29.3 | 218.8 | 1926.7 | [6 empty] | OUTUM | [6 empty] | Exit umbra
1994-03-24 03:12 | 1:23 |  | -30 | 218.8 | 1910.3 | [6 empty] | OUTPM | [6 empty] | Exit penumbra
1994-03-24 03:12 | 1:23 |  | -30 | 218.8 | 1909.2 | [6 empty] | S30D
Standard Prep1 Script
1994-03-24 03:13 | 1:24 | 0 | [10 empty] | NIR camera & cryocooler ON; SA mode to AUTO
End Prep1 Script
1994-03-24 03:22 | 1:32 |  | -40 | 218.8 | 1670.4 | [6 empty] | S40D
1994-03-24 03:23 | 1:33 | [9 empty] | MAD | LOS
Standard Prep2 Script
1994-03-24 03:24 | 1:34 | 0 | [10 empty] | LWIR camera & cryocooler ON; Laser heater ON; Open sensor door if closed
End Prep2 Script
#VALUE!
1994-03-24 03:29 | 1:40 | 0 | [10 empty] | Msg "WRNG: Omni/2k in 1 min.."
1994-03-24 03:30 | 1:40 |  | -50 | 218.9 | 1447.4 | [6 empty] | S50D
1994-03-24 03:30 | 1:41 | 60 | [10 empty] | SSDR to IDLE; Switch to 2 kbps bypass mode
1994-03-24 03:31 | 1:42 | 60 | [10 empty] | Switch to omni antennas
1994-03-24 03:32 | 1:43 | 60 | [10 empty] | Select ST-B; Set SA step rate to HI; Slew s/c sensors to Crux (ACSMode=StarPointing, Index=3) | [5 empty] | Slew to Crux
1994-03-24 03:33 | 1:43 | 30 | [10 empty] | UV & HR cameras ON
1994-03-24 03:37 | 1:48 |  | -60 | 219.1 | 1245.3 | [6 empty] | S60D
1994-03-24 03:42 | 1:52 | 545 | [10 empty] | Initialize filters (DHU SEQT 27); Record in SSDR Segment 1; Load Crux exposure table (LUNCRUX) | [5 empty] | Start SSDR in Segment 1
1994-03-24 03:42 | 1:53 | 25 | [10 empty] | Perform NIR imaging (DHU SEQT 31) | [5 empty] | Dark Field imaging starts
1994-03-24 03:42 | 1:53 | 12 | [10 empty] | Stop imaging - select ST-B
1994-03-24 03:44 | 1:54 | 72 | [10 empty] | Perform UV0 imaging (DHU SEQT 29)
1994-03-24 03:44 | 1:54 |  | -70 | 219.5 | 1066.8 | [6 empty] | S70D
1994-03-24 03:44 | 1:54 | 12 | [10 empty] | Perform HR imaging (DHU SEQT 30)
1994-03-24 03:44 | 1:54 | 12 | [10 empty] | Perform LWIR imaging (DHU SEQT 25)
1994-03-24 03:44 | 1:55 | 12 | [10 empty] | Perform NIR imaging (DHU SEQT 31)
1994-03-24 03:44 | 1:55 | 12 | [10 empty] | #VALUE! | [5 empty] | Slew to nadir (inertial pointing)
1994-03-24 03:45 | 1:55 | 30 | [10 empty] | Laser Power ON
#VALUE!
1994-03-24 03:49 | 2:00 |  | -80 | 220.9 | 912.5 | [6 empty] | S80D
#VALUE!
1994-03-24 03:52 | 2:03 | 0 | [10 empty] | Initialize filters (DHU SEQT 28); Load exposure table LUNARZ85S; Load exposure table LUNNIR85
1994-03-24 03:53 | 2:04 | 60 | [10 empty] | Switch to lunar mapping mode (ACSMode=LunarMapping); Start Imaging (DHU SEQT 9) | [5 empty] | START MAPPING
1994-03-24 03:54 | 2:05 | 60 | -89.5 | 309.1 | 782 | [6 empty] | South Pole | Set SA step rate to LO
1994-03-24 03:55 | 2:05 |  | -88.7 | 17 | 767.5 | [6 empty] | LDAWN
1994-03-24 03:59 | 2:09 | 278 | -80 | 35.3 | 674.4 | [6 empty] | S80A | Load exposure table LUNARZ75S; Load Exposure table LUNNIR75; Select DHU SEQT 3
1994-03-24 04:03 | 2:14 | 256 | -70 | 36.7 | 588 | [6 empty] | S70A | Load exposure table LUNARZ65S; Load Exposure table LUNNIR65; Select DHU SEQT 4
1994-03-24 04:07 | 2:18 | 241 | -60 | 37.2 | 521.8 | [6 empty] | S60A | Load exposure table LUNARZ55S; Select DHU SEQT 6
1994-03-24 04:11 | 2:22 | 229 | -50 | 37.4 | 474.9 | [6 empty] | S50A | Record in SSDR Segment 2; Load exposure table LUNARZ45S; Select DHU SEQT 5 | [5 empty] | SSDR Segment 2 HiRes imaging stopped by gain setting in exposure table
1994-03-24 04:15 | 2:25 | 221 | -40 | 37.5 | 446.3 | [6 empty] | S40A | Load exposure table LUNARZ35S
1994-03-24 04:18 | 2:29 | 217 | -30 | 37.6 | 435.6 | [6 empty] | S30A | Load exposure table LUNARZ25S
1994-03-24 04:19 | 2:29 |  | -28.9 | 37.6 | 435.5 | [6 empty] | Periselene
1994-03-24 04:22 | 2:32 | 217 | -20 | 37.7 | 442.6 | [6 empty] | S20A | Load exposure table LUNARZ15S
1994-03-24 04:26 | 2:36 | 220 | -10 | 37.7 | 467.3 | [6 empty] | S10A | Load exposure table LUNARZ05S; Select DHU SEQT 6
1994-03-24 04:29 | 2:40 | 226 | 0 | 37.8 | 510.4 | [6 empty] | Equator - A | Record in SSDR Segment 3; Load exposure table LUNARZ05N; Select DHU SEQT 7 | [5 empty] | SSDR Segment 3
1994-03-24 04:33 | 2:44 | 238 | 10 | 37.8 | 572.4 | [6 empty] | N10A | Load CEQ_08U.UMI into SEQT 8; Load exposure table LUNARZ15N; Select DHU SEQT 8 | [5 empty] | UV and IR uncompressed
1994-03-24 04:38 | 2:48 | 253 | 20 | 37.9 | 654.4 | [6 empty] | N20A | Load exposure table LUNARZ25N; Select DHU SEQT 9 | [5 empty] | Resume compression
1994-03-24 04:39 | 2:49 | 60 | [10 empty] | Laser power OFF
1994-03-24 04:42 | 2:53 | 213 | 30 | 37.9 | 757.5 | [6 empty] | N30A | Load exposure table LUNARZ35N; Select DHU SEQT 10
1994-03-24 04:47 | 2:58 | 299 | 40 | 38 | 883.2 | [6 empty] | N40A | Record in SSDR Segment 4; Load exposure table LUNARZ45N; Select DHU SEQT 11 | [5 empty] | SSDR Segment 4
1994-03-24 04:53 | 3:03 | 333 | 50 | 38.1 | 1032.3 | [6 empty] | N50A | Load exposure table LUNARZ55N; Select DHU SEQT 12 | [5 empty] | Resume HiRes imaging
1994-03-24 04:59 | 3:09 | 373 | 60 | 38.3 | 1205.7 | [6 empty] | N60A | Load exposure table LUNARZ65N; Load exposure table LUNNIR65; Select DHU SEQT 13
1994-03-24 05:06 | 3:16 | 424 | 70 | 38.7 | 1403 | [6 empty] | N70A | Load exposure table LUNARZ75N; Load Exposure table LUNNIR75; Select DHU SEQT 14
1994-03-24 05:14 | 3:24 | 483 | 80 | 40 | 1622 | [6 empty] | N80A | Load exposure table LUNARZ85N; Load Exposure table LUNNIR85; Select DHU SEQT 15
1994-03-24 05:15 | 3:25 | 60 | [10 empty] | Load EEQ_08.UMI into SEQT 08 | [5 empty] | Restore compressed SEQT 8
#VALUE!
1994-03-24 05:23 | 3:34 |  | 89.5 | 128.2 | 1858 | [6 empty] | North Pole
Standard Post Script
1994-03-24 05:24 | 3:35 | 0 | [10 empty] | Stop Imaging - select ST-B
1994-03-24 05:24 | 3:35 | 5 | [10 empty] | Set SA step rate to HI; Slew s/c sensors to Vega (GNC12VEGA); Laser power OFF; Load Vega exposure tables (LUNVEGA) | [5 empty] | Slew to Vega (inertial pointing)
1994-03-24 05:25 | 3:35 |  | 88.7 | 196.6 | 1887.9 | [6 empty] | LDUSK
1994-03-24 05:27 | 3:38 | 180 | [10 empty] | Park opaque filter on HiRes (DHU SEQT 27)
1994-03-24 05:28 | 3:38 | 15 | [10 empty] | Select ST-B; Activate waitwhileslew for 400 sec
1994-03-24 05:28 | 3:39 | 41 | [10 empty] | Perform UVO Imaging (DHU SEQT 29) | [5 empty] | Start calibration imaging
1994-03-24 05:29 | 3:39 | 12 | [10 empty] | Perform LWIR imaging (DHU SEQT 25)
1994-03-24 05:29 | 3:39 | 12 | [10 empty] | Perform NIR imaging (DHU SEQT 31)
1994-03-24 05:29 | 3:39 | 6 | [10 empty] | Load exposure table LUNIRDKS1
1994-03-24 05:29 | 3:39 | 6 | [10 empty] | Load exposure table LUNIRDKS2
1994-03-24 05:29 | 3:39 | 6 | [10 empty] | Perform HiRes Imaging (DHU SEQT 30) | [5 empty] | One image only, filter 1
1994-03-24 05:29 | 3:40 | 6 | [10 empty] | Open ST-B door if closed; Stop imaging - select ST-B; UV & HR cameras OFF; IR cameras & cryocoolers OFF; Slew s/c HGA to Earth (ACSMode=EarthPointing, Center); Activate waitwhile slew for 360 sec | [5 empty] | Slew HGA to Earth with active waitwhileslew
1994-03-24 05:32 | 3:42 | 173 | [10 empty] | Switch to HGA | [5 empty] | READY FOR DATA DUMP - Time approximate. Earlier than plan because of waitwhileslew
End Post Script
1994-03-24 05:33 | 3:43 | [11 empty] | Switch to DHU mode @ 128 kbps | [5 empty] | Ground Command
1994-03-24 05:34 | 3:44 |  | 80 | 214.5 | 2102.5 | [6 empty] | N80D
1994-03-24 05:34 | 3:44 | [11 empty] | Downlink SSDR Segment 1 | [5 empty] | Ground Command
1994-03-24 05:39 | 3:49 | [11 empty] | Uplink and schedule L155 scripts | [5 empty] | Ground Command
1994-03-24 05:46 | 3:56 |  | 70 | 215.8 | 2343.9 | [6 empty] | N70D
1994-03-24 05:59 | 4:10 |  | 60 | 216.2 | 2564.8 | [6 empty] | N60D
1994-03-24 06:11 | 4:21 | [11 empty] | Downlink SSDR Segment 2 | [5 empty] | Ground Command
1994-03-24 06:14 | 4:24 |  | 50 | 216.3 | 2745.9 | [6 empty] | N50D
1994-03-24 06:30 | 4:40 |  | 40 | 216.3 | 2867.9 | [6 empty] | N40D
1994-03-24 06:44 | 4:54 | [9 empty] | CAN | AOS
1994-03-24 06:45 | 4:55 | [11 empty] | Downlink SSDR Segment 3 | [5 empty] | Ground Command
1994-03-24 06:46 | 4:57 |  | 30 | 216.3 | 2916.1 | [6 empty] | N30D
1994-03-24 06:48 | 4:58 |  | 29 | 216.3 | 2916.6 | [6 empty] | Aposelene