## Sheet1
UTC Time | Orbit Time (h:mm:ss) | Time Since Previous Event (sec) | Lat. (deg) | Long. (deg) | Altitude (km) | POMONKEY | GOLDSTONE | CANBERRA | MADRID | Sun Shadow | Site | Orbital Event | S/C Command Activities | UV/Vis | HiRes | NIR | LWIR | Laser | Comment
1994-02-14 | [12 empty] | Pointing accuracy test, auto-exposure test using the Earth, and a star occultation observation planned | [5 empty] | No scheduled SCL scripts, all ground commands.
1994-02-14 02:28 | [10 empty] | MAD | LOS
1994-02-14 03:38 | [12 empty] | Read Dosimeter
1994-02-14 03:45 | [12 empty] | Expose Dosimeter
1994-02-14 04:37 | [12 empty] | Read Dosimeter
1994-02-14 04:37 | [12 empty] | Read Dosimeter
1994-02-14 04:38 | [12 empty] | Read Dosimeter
1994-02-14 04:45 | [12 empty] | Expose Dosimeter
1994-02-14 06:00 | [12 empty] | Read Dosimeter
1994-02-14 06:08 | [12 empty] | Expose Dosimeter
1994-02-14 06:42 | [10 empty] | CAN | AOS
1994-02-14 07:00 | [12 empty] | Read Dosimeter
1994-02-14 07:06 | [12 empty] | Expose Dosimeter
1994-02-14 08:19 | [10 empty] | PMK | LOS
1994-02-14 08:43 | [12 empty] | RANGE A ON
Begin Pointing Accuracy Test
1994-02-14 08:56 | [12 empty] | Slew S/C sensors to Vega (VEGAFEB13)
1994-02-14 09:02 | [12 empty] | Read Dosimeter
1994-02-14 09:08 | [12 empty] | Expose Dosimeter
1994-02-14 09:14 | [12 empty] | Slew S/C sensors to Vega (VEGAFEB14)
1994-02-14 09:18 | [12 empty] | Open Sensor Door
1994-02-14 09:21 | [12 empty] | UVVIS Camera ON
1994-02-14 09:22 | [12 empty] | HIRES Camera On
1994-02-14 09:25 | [12 empty] | Record in SSDR 1
1994-02-14 09:26 | [12 empty] | Hires Realtime Image Capture, Very Low settings (DHU36_LIDVL) | [5 empty] | Filter 5
1994-02-14 09:28 | [10 empty] | GDS | LOS
1994-02-14 09:36 | [12 empty] | UVVIS Realtime Image Capture (DHU36_UVVUSM)
1994-02-14 09:38 | [12 empty] | Uplink DHU Sequence SEQ_HR_266
1994-02-14 09:39 | [12 empty] | Uplink DHU Sequence SEQ_10
1994-02-14 09:40 | [12 empty] | Uplink Exposure Table POINTING_2MS_EXP; Initialize Filters (DHUSEL26); DHUSELNO
1994-02-14 09:40 | [12 empty] | DHUSEL10
1994-02-14 09:42 | [12 empty] | Activate ST-A (DHUSEL1);
1994-02-14 09:43 | [12 empty] | Close Sensor Door
1994-02-14 09:43 | [12 empty] | Turn OFF UV/VIS and Hires Cameras
End Pointing Accuracy Test
1994-02-14 10:00 | [12 empty] | Read Dosimeter
1994-02-14 10:05 | [12 empty] | Expose Dosimeter
1994-02-14 10:44 | [12 empty] | Read Dosimeter
1994-02-14 10:49 | [12 empty] | Expose Dosimeter
1994-02-14 10:55 | [12 empty] | Switch to DHU mode @ 64 kbps
1994-02-14 11:00 | [12 empty] | Slew S/C to Earth (GNC13CANRW)
1994-02-14 11:09 | [12 empty] | Range B ON
1994-02-14 11:13 | [12 empty] | Switch to DHU Mode @128 kbps
1994-02-14 11:17 | [12 empty] | Download SSDR Segment 1
1994-02-14 11:50 | [12 empty] | Read Dosimeter
1994-02-14 11:54 | [12 empty] | Expose Dosimeter
1994-02-14 12:53 | [10 empty] | CAN | LOS
1994-02-14 13:27 | [10 empty] | MAD | AOS
1994-02-14 14:23 | [12 empty] | Slew S/C to Madrid Station (GNC13MADRW)
1994-02-14 14:24 | [12 empty] | Read Dosimeter
1994-02-14 14:30 | [12 empty] | Expose Dosimeter
1994-02-14 16:09 | [12 empty] | Read Dosimeter
1994-02-14 16:17 | [12 empty] | Expose Dosimeter
1994-02-14 16:22 | [12 empty] | Read Dosimeter
1994-02-14 16:43 | [12 empty] | Switch to DHU Mode @128 kbps
Begin Earth Observation Test Autoexposure & Centroiding
1994-02-14 17:06 | [12 empty] | Slew S/C to Center on Pleiades (CEXL GNC18,STARIDX=2) | [5 empty] | "Star pointing" ACS mode, Center target = Pleiades
1994-02-14 17:09 | [12 empty] | NIR Camera ON
1994-02-14 17:09 | [12 empty] | Hires Camera ON
1994-02-14 17:10 | [12 empty] | UV/Vis Camera ON
1994-02-14 17:10 | [12 empty] | LWIR Camera ON
1994-02-14 17:13 | [12 empty] | Open Sensor Door
1994-02-14 17:15 | [12 empty] | Uplink Exposure Table: EXPDAY3
1994-02-14 17:16 | [12 empty] | Uplink Sequence Table; SEQ_22
1994-02-14 17:20 | [10 empty] | PMK | AOS
1994-02-14 17:28 | [12 empty] | DHUSELNO
1994-02-14 17:29 | [12 empty] | Expose Dosimeter
1994-02-14 17:28 | [12 empty] | Initialize Filter Positions; DHUSEL27
1994-02-14 17:30 | [12 empty] | DHUSEL1
1994-02-14 17:32 | [12 empty] | Request Real-time Image (DUMP_UV14)
1994-02-14 17:32 | [12 empty] | DHUSEL22
1994-02-14 17:34 | [12 empty] | Activate ST-A (DHUSEL1);
1994-02-14 17:35 | [12 empty] | Request Real-time Image (DUMP_UV14)
1994-02-14 17:36 | [12 empty] | DHUSEL22
1994-02-14 17:36 | [12 empty] | Activate ST-A (DHUSEL1);
1994-02-14 17:38 | [12 empty] | Request Real-time Image (DUMP_UV14) | [5 empty] | Verify Earth in FOV
1994-02-14 17:38 | [12 empty] | DHUSEL22
1994-02-14 17:39 | [12 empty] | Activate ST-A (DHUSEL1);
1994-02-14 17:41 | [12 empty] | Activate Autoexposure (AE_UV14,AE_N1, AE_L)
1994-02-14 17:42 | [12 empty] | Request Real-time Image (DUMP_N1)
1994-02-14 17:42 | [12 empty] | DHUSEL22
1994-02-14 17:43 | [12 empty] | Request Real-time Image (DUMP_N1)
1994-02-14 17:45 | [12 empty] | Activate Centroiding on All Cameras (CENTRD_UV14, CNTRD,H4_CNTRD_N1,CNTRD_L)
1994-02-14 17:47 | [12 empty] | Slew S/C to center in UVV (GNC1E, Camera=UV-VIS1)
1994-02-14 17:49 | [12 empty] | Request Real-time Image (DUMP_N1)
DE-Activate Centroiding on IR Cameras, AE_N1,CTL=D,AE_L,CTL=D)
1994-02-14 17:54 | [12 empty] | DHUSEL22
1994-02-14 17:55 | [12 empty] | Activate ST-A (DHUSEL1);
1994-02-14 17:58 | [12 empty] | Activate AutoExposure of UV
1994-02-14 17:58 | [12 empty] | De-Activate AutoExpossure for UV
1984-02-14 17:58 | [12 empty] | De-Activate Centroiding for UV
1994-02-14 17:59 | [12 empty] | DHUSELNO
1994-02-14 17:59 | [12 empty] | Activate ST-A (DHUSEL1);
1994-02-14 18:09 | [12 empty] | Turn OFF NIR and LWIR Cameras
1994-02-14 18:13 | [12 empty] | Close Sensor Door
1994-02-14 18:14 | [12 empty] | DHUSELNO
1994-02-14 18:14 | [12 empty] | Re-Initialize Filters; DHUSEL27
1994-02-14 18:14 | [12 empty] | Activate ST-A (DHUSEL1);
End Earth Observation, Autoexposure & Centroiding Test
1994-02-14 18:29 | [12 empty] | Read Dosimeter
1994-02-14 18:34 | [12 empty] | Expose Dosimeter
1994-02-14 18:39 | [12 empty] | Slew S/C to Center Cameras on Earth (GNC12)
1994-02-14 19:02 | [12 empty] | DHUSELNO
1994-02-14 19:02 | [12 empty] | Reset SIP
1994-02-14 19:03 | [12 empty] | Turn OFF Hires & UV/VIS
1994-02-14 19:09 | [12 empty] | Activate ST-A (DHUSEL1);
1994-02-14 19:14 | [12 empty] | Slew S/C (GNC11)
1994-02-14 19:15 | [12 empty] | Slew S/C (GNC33)
1994-02-14 19:16 | [12 empty] | Slew S/C to Center Cameras on Earth (GNC12)
1994-02-14 19:34 | [12 empty] | Read Dosimeter
1994-02-14 19:40 | [12 empty] | Expose Dosimeter
1994-02-14 20:40 | [12 empty] | Read Dosimeter
1994-02-14 20:45 | [12 empty] | Expose Dosimeter
Begin Occultation Test
1994-02-14 20:44 | [12 empty] | Open Sensor Door
1994-02-14 20:48 | [12 empty] | Turn ON HIRES & UV/VIS Cameras
1994-02-14 20:49 | [12 empty] | Record in SSDR Segment 2
1994-02-14 20:51 | [12 empty] | Upload Exposure Table; P2OCCULT2
1994-02-14 20:51 | [12 empty] | Upload Sequence Table; AEQIL_263
1994-02-14 20:52 | [12 empty] | Upload Sequence Table; DHUIL1
1994-02-14 20:54 | [12 empty] | DHUSELNO
1994-02-14 20:55 | [12 empty] | Initialize Filters; DHUSEL26
1994-02-14 20:55 | [12 empty] | DHUSEL14
1994-02-14 21:01 | [12 empty] | DHUSELNO
1994-02-14 21:02 | [12 empty] | Activate ST-A (DHUSEL1);
1994-02-14 21:02 | [12 empty] | Close Sensor Door
1994-02-14 21:03 | [12 empty] | Turn OFF Hires & UVVIS Cameras
End Occultation Test
1994-02-14 21:06 | [12 empty] | Slew S/C to Center on Earth (GNC12)
1994-02-14 21:24 | [12 empty] | Downlink SSDR Segment 1
1994-02-14 21:45 | [12 empty] | Read Dosimeter
1994-02-14 21:50 | [12 empty] | Expose Dosimeter
1994-02-14 21:39 | [12 empty] | Downlink SSDR Segment 2
1994-02-14 21:50 | [10 empty] | GDS | AOS
1994-02-14 22:51 | [12 empty] | Read Dosimeter
1994-02-14 23:57 | [12 empty] | Slew S/C (GNC12P2)