## Sheet1
UTC Time | Orbit Time (h:mm:ss) | Time Since Previous Event (sec) | Lat. (deg) | Long. (deg) | Altitude (km) | POMONKEY | GOLDSTONE | CANBERRA | MADRID | Sun Shadow | Site | Orbital Event | S/C Command Activities | UV/Vis | HiRes | NIR | LWIR | Laser | Comment
1994-02-15 | [18 empty] | P2 burn by scheduled SCL script, all else ground commands.
1994-02-15 00:01 | [10 empty] | MAD | LOS
1994-02-15 03:01 | [12 empty] | Read Dosimeter
1994-02-15 03:07 | [12 empty] | Expose Dosimeter
1994-02-15 03:39 | [10 empty] | CAN | AOS
1994-02-15 03:48 | [12 empty] | Read Dosimater
1994-02-15 03:54 | [12 empty] | Expose Doseimter
1994-02-15 03:57 | [12 empty] | Expose Dosimeter
1994-02-15 04:41 | [12 empty] | Read Dosimeter
1994-02-15 04:46 | [12 empty] | Expose Dosimeter
1994-02-15 05:19 | [10 empty] | PMK | LOS
1994-02-15 05:49 | [12 empty] | Slew S/C to P2 burn attitude (GNC12P2)
1994-02-15 06:27 | [12 empty] | Read Dosimeter
1994-02-15 06:32 | [12 empty] | Expose Dosimeter
1994-02-15 07:00 | [12 empty] | Read Dosimeter
1994-02-15 07:05 | [12 empty] | Expose Dosimeter
1994-02-15 07:39 | [12 empty] | Read Dosimeter
1994-02-15 07:44 | [12 empty] | Expose Dosimeter
1994-02-15 08:00 | [10 empty] | GDS | LOS
P2 Burn
1994-02-15 08:14 | [12 empty] | Slew S/C to updated P2 burn attitude (GNC12P2RW)
1994-02-15 08:50 | [12 empty] | Uplink and Schedule P2 burn scripts
1994-02-15 09:05 | [12 empty] | Expose Dosimeter
1994-02-15 09:10 | [12 empty] | Read Dosimeter
1994-02-15 09:22 | [12 empty] | Expose Dosimeter
1994-02-15 09:23 | [12 empty] | Read Dosimeter
1994-02-15 09:53 | [12 empty] | Expose Dosimeter
1994-02-15 09:58 | [12 empty] | Read Dosimeter
1994-02-15 10:18 | [12 empty] | Record TLM in SSDR Segment 0
1994-02-15 11:36 | [12 empty] | IMU B On
1994-02-15 12:53 | [12 empty] | P2 BURN
P2 burn Complete
1994-02-15 12:56 | [10 empty] | MAD | AOS
1994-02-15 13:37 | [10 empty] | CAN | LOS
1994-02-15 15:46 | [12 empty] | IMU B Off
1994-02-15 15:56 | [12 empty] | Slew S/C to sun soaking attitude (GNC12SUNRW)
1994-02-15 15:59 | [12 empty] | IMU B On
1994-02-15 15:59 | [12 empty] | Slew S/C HGA to MAD (GNC12MADRW)
1994-02-15 16:41 | [12 empty] | Switch to DHU mode @ 8 kbps
1994-02-15 16:45 | [12 empty] | Switch to DHU mode @ 128 kbps
1994-02-15 16:56 | [12 empty] | Downlink SSDR Segment 0
1994-02-15 17:18 | [12 empty] | Downlink SSDR Segment 2
1994-02-15 17:31 | [12 empty] | Downlink SSDR Segment 3
1994-02-15 17:44 | [10 empty] | PMK | AOS
1994-02-15 17:59 | [12 empty] | Downlink SSDR Segment 4
1994-02-15 18:42 | [12 empty] | Downlink SSDR Segment 5
1994-02-15 20:06 | [12 empty] | Downlink SSDR Segment 6
1994-02-15 20:31 | [10 empty] | GDS | AOS
1994-02-15 20:54 | [12 empty] | Downlink SSDR Segment 2
Begin Earth Observation #8
1994-02-15 21:15 | [12 empty] | Turn ON NIR, LWIR, UV/VIS, Hires Cameras
1994-02-15 21:43 | [12 empty] | Uplink Exposure Tables; (EXPDAY3)
1994-02-15 21:44 | [12 empty] | Uplink Sequence Table; SEQ_262
1994-02-15 21:45 | [12 empty] | Initialize Filters; DHUSEL26
1994-02-15 21:45 | [12 empty] | Activate ST-A (DHUSEL1);
1994-02-15 21:46 | [12 empty] | OPEN SENSOR DOOR
1994-02-15 22:15 | [12 empty] | Record in SSDR Segment 1
1994-02-15 22:22 | [12 empty] | Request Realtime Image (DUMP_UV14)
1994-02-15 22:23 | [12 empty] | DHUSEL0
1994-02-15 22:23 | [12 empty] | Activate ST-A (DHUSEL1);
1994-02-15 22:24 | [12 empty] | Request Realtime Image (DUMP_UV14)
1994-02-15 22:25 | [12 empty] | Activate AutoExposure for UV/VIS, NIR, LWIR (AE_UV14,AE_N1,AE_L)
1994-02-15 22:25 | [12 empty] | DHUSEL0
1994-02-15 22:27 | [12 empty] | Request Realtime Image (DUMP_UV14)
1994-02-15 22:28 | [12 empty] | Activate ST-A (DHUSEL1);
1994-02-15 22:29 | [12 empty] | Request Realtime Image (DUMP_UV14)
1994-02-15 22:30 | [12 empty] | Activate Centroiding for UV/Vis, Hires (CNTRD_UV14,CNTRD,H4)
1994-02-15 22:30 | [12 empty] | DHUSEL0
1994-02-15 22:32 | [12 empty] | Activate Centroiding for NIR (CNTRD_N1)
1994-02-15 22:33 | [12 empty] | Request Realtime Image; (DUMP_N1)
1994-02-15 22:33 | [12 empty] | Activate Centroiding for LWIR (CNTRD_L)
1994-02-15 22:34 | [12 empty] | Activate ST-A (DHUSEL1);
1994-02-15 22:35 | [12 empty] | De-Activate Centroiding for UV/VIS, HIRES,NIR,LWIR
1994-02-15 22:36 | [12 empty] | DHUSEL27
1994-02-15 22:38 | [12 empty] | Activate ST-A (DHUSEL1);
Turn off AutoExposure
1994-02-15 22:48 | [12 empty] | Close Sensor Door
1994-02-15 22:48 | [12 empty] | Turn off LWIR,NIR,UV/VIS,HIRES
1994-02-15 22:56 | [12 empty] | Slew S/C to Sun-Soaked (GNC12SUNRW)
End Earth Observation #8